## Change Order
Change Order Template
Contract Modification Request
One row per cost component. The Pricing Summary block totals the change order amount. Capture both cost and schedule impact.
CO # | Description | Reason | Quantity | Unit | Unit Cost | Total Cost | Schedule Impact (days)
Change Order #007 - Owner-Directed Scope Addition
007.01 | Additional electrical receptacles for tenant equipment | Owner Request | 12 | EA | 285 | 3420 | 0
007.02 | Upgrade conference room AV rough-in | Owner Request | 1 | LS | 4850 | 4850 | 1
007.03 | Add data drops at reception and pantry | Owner Request | 6 | EA | 220 | 1320 | 0
007.04 | Sound mass loaded vinyl at conference walls | Owner Request | 460 | SF | 8.5 | 3910 | 2
007.05 | Premium hardware upgrade per Owner selection | Owner Request | 14 | EA | 175 | 2450 | 0
007.06 | General conditions impact and supervision | Indirect | 1 | LS | 1850 | 1850 | 0
007.07 | Subcontractor markup at 10% | Markup | 1 | LS | 1580 | 1580 | 0
007.08 | Contractor overhead and profit at 15% | Markup | 1 | LS | 2920 | 2920 | 0
Pricing Summary
Original Contract Sum | [6 empty] | 1630000
Sum of Previous Change Orders | [6 empty] | 38500
This Change Order
New Contract Sum
New Substantial Completion (days added) | [6 empty] | 3
Template by BuildVision AI - buildvisionai.com - Generate this automatically with AI: https://buildvisionai.com

## How To Use
How to use the Change Order Template
1. | Issue change orders only with written authorization.
2. | Document scope, cost, and schedule impact for each change.
3. | Get pricing from affected subcontractors before submission.
4. | Apply contractor markup per the contract terms.
5. | Track new contract sum after each approved change order.
Template by BuildVision AI - buildvisionai.com - Generate this automatically with AI: https://buildvisionai.com