## Contract
Construction Contract Template
Owner-Contractor Agreement
This template summarizes the contractual terms between the Owner and Contractor. Each row represents a clause that should appear in the executed agreement. Replace bracketed placeholders with project-specific values.
Article | Clause | Terms | Reference
Parties and Project
1 | Parties | Owner: [Owner Legal Name]; Contractor: [Contractor Legal Name]; effective [Date] | Page 1
2 | Project | Construction of [Project Name] at [Project Address] | Exhibit A
Scope and Documents
3 | Scope of Work | Contractor shall furnish all labor, materials, equipment, and services per Contract Documents | Exhibit B
4 | Contract Documents | Agreement, drawings dated [Date], specifications, addenda, and signed change orders | Exhibit C
Price and Payment
5 | Contract Sum | Lump Sum of $[Amount], subject to additions and deductions per change orders | Exhibit D
6 | Progress Payments | Monthly applications for payment, due net 30 days after approval | Article 6
7 | Retainage | 5% retained until substantial completion, full release at final completion | Article 6
Schedule
8 | Commencement | Within 10 days of Notice to Proceed | Article 7
9 | Substantial Completion | [Number] calendar days from commencement | Article 7
10 | Liquidated Damages | $[Amount] per calendar day of delay beyond Substantial Completion | Article 7
Risk and Compliance
11 | Insurance | GL $2M occurrence / $4M aggregate; WC statutory; Auto $1M; Builders Risk by Owner | Exhibit E
12 | Indemnification | Mutual indemnity for negligent acts, subject to comparative fault | Article 9
13 | Warranty | One-year correction period from Substantial Completion; manufacturer warranties pass through | Article 10
14 | Change Orders | Written orders required; price impact within 10 business days of issuance | Article 11
15 | Dispute Resolution | Mediation, then binding arbitration in [State] under AAA Construction Rules | Article 12
16 | Termination | For cause with 7-day cure; for convenience with payment for work performed plus reasonable termination costs | Article 13
17 | Governing Law | Laws of the State of [State], venue in [County] | Article 14
18 | Notices | Written notices to addresses listed; email permitted with confirmation | Article 15
Template by BuildVision AI - buildvisionai.com - Generate this automatically with AI: https://buildvisionai.com

## How To Use
How to use the Construction Contract Template
1. | Review the contract with legal counsel before execution.
2. | Replace every bracketed placeholder with project-specific values.
3. | Attach the Exhibits referenced in each clause.
4. | Obtain signatures from authorized representatives of both parties.
5. | Distribute fully executed copies to all stakeholders.
Template by BuildVision AI - buildvisionai.com - Generate this automatically with AI: https://buildvisionai.com