## Invoice
Construction Invoice Template
Application for Payment
Use one row per pay item. Update Work Completed This Period and Stored Materials each cycle. Retainage and Net Due are calculated in the Pricing Summary.
Item # | Description | Scheduled Value | Previous Completed | This Period | Stored Materials | Total to Date | % Complete
001 | General Conditions | 145000 | 72500 | 14500 | 0 | 87000 | 60%
002 | Site Preparation | 95000 | 95000 | 0 | 0 | 95000 | 100%
003 | Foundations | 165000 | 165000 | 0 | 0 | 165000 | 100%
004 | Concrete Slabs | 85000 | 68000 | 17000 | 0 | 85000 | 100%
005 | Structural Steel | 245000 | 196000 | 49000 | 0 | 245000 | 100%
006 | Rough Carpentry | 78000 | 58500 | 19500 | 0 | 78000 | 100%
007 | Roofing | 145000 | 36250 | 72500 | 14500 | 123250 | 85%
008 | Exterior Walls | 195000 | 78000 | 78000 | 0 | 156000 | 80%
009 | Windows and Doors | 85000 | 0 | 25500 | 17000 | 42500 | 50%
010 | Plumbing Rough | 92000 | 64400 | 18400 | 0 | 82800 | 90%
011 | HVAC Rough | 158000 | 79000 | 47400 | 0 | 126400 | 80%
012 | Electrical Rough | 142000 | 71000 | 35500 | 0 | 106500 | 75%
Pricing Summary
Original Contract Sum | [6 empty] | 1630000
Approved Change Orders | [6 empty] | 38500
Revised Contract Sum
Total Completed and Stored | [6 empty] | 1391950
Retainage (5%)
Less Previous Payments | [6 empty] | 894500
Current Payment Due
Template by BuildVision AI - buildvisionai.com - Generate this automatically with AI: https://buildvisionai.com

## How To Use
How to use the Construction Invoice Template
1. | Use the same Schedule of Values for every pay application.
2. | Update Work This Period and Stored Materials columns each cycle.
3. | Total to Date equals Previous + This Period + Stored Materials.
4. | Retainage is typically 5 to 10 percent of work completed.
5. | Submit with lien waivers and supporting documentation.
Template by BuildVision AI - buildvisionai.com - Generate this automatically with AI: https://buildvisionai.com