## Schedule
Construction Schedule Template
Project Schedule with Predecessors
Each row is one task. Set the duration, start, and finish dates and list predecessor task IDs. Use this as input to a Gantt chart in your scheduling tool.
ID | Task | Duration (days) | Start | Finish | Predecessor | Resource | Status
Pre-Construction
10 | Notice to Proceed | 0 | 2026-04-06 | 2026-04-06 |  | Owner | Complete
20 | Permits and submittals | 15 | 2026-04-06 | 2026-04-24 | 10 | PM | Complete
30 | Mobilize site | 5 | 2026-04-27 | 2026-05-01 | 20 | Superintendent | Complete
Site and Foundations
40 | Site clearing and grading | 8 | 2026-05-04 | 2026-05-13 | 30 | Sitework Sub | Complete
50 | Excavate footings | 5 | 2026-05-14 | 2026-05-20 | 40 | Sitework Sub | In Progress
60 | Form, rebar, place footings | 10 | 2026-05-21 | 2026-06-03 | 50 | Concrete Crew | Pending
70 | Foundation walls | 12 | 2026-06-04 | 2026-06-19 | 60 | Concrete Crew | Pending
Structure
80 | Steel erection | 18 | 2026-06-22 | 2026-07-15 | 70 | Steel Sub | Pending
90 | Metal deck and floor pour | 8 | 2026-07-16 | 2026-07-27 | 80 | Concrete Crew | Pending
100 | Roof framing | 12 | 2026-07-28 | 2026-08-12 | 90 | Carpentry | Pending
Envelope and MEP Rough
110 | Roofing membrane | 10 | 2026-08-13 | 2026-08-26 | 100 | Roofing Sub | Pending
120 | Exterior walls and windows | 22 | 2026-08-13 | 2026-09-11 | 100 | Multiple | Pending
130 | Plumbing rough | 18 | 2026-08-13 | 2026-09-07 | 100 | Plumbing Sub | Pending
140 | HVAC rough | 20 | 2026-08-13 | 2026-09-09 | 100 | Mechanical Sub | Pending
150 | Electrical rough | 22 | 2026-08-13 | 2026-09-11 | 100 | Electrical Sub | Pending
Interior Finishes and Closeout
160 | Drywall and paint | 25 | 2026-09-14 | 2026-10-16 | 120,130,140,150 | Multiple | Pending
170 | Flooring and finishes | 18 | 2026-10-19 | 2026-11-11 | 160 | Multiple | Pending
180 | MEP trim and commissioning | 15 | 2026-11-02 | 2026-11-20 | 160 | Multiple | Pending
190 | Punch list and substantial completion | 12 | 2026-11-23 | 2026-12-08 | 170,180 | GC | Pending
Template by BuildVision AI - buildvisionai.com - Generate this automatically with AI: https://buildvisionai.com

## How To Use
How to use the Construction Schedule Template
1. | Set your Notice to Proceed date and update all subsequent dates.
2. | Use predecessor IDs to define task dependencies.
3. | Mark status as Pending, In Progress, Complete, or Delayed.
4. | Re-baseline the schedule monthly with actual progress.
5. | Import this sheet into Microsoft Project or Primavera if needed.
Template by BuildVision AI - buildvisionai.com - Generate this automatically with AI: https://buildvisionai.com