## Punch List
Punch List Template
Closeout Deficiencies Log
Track closeout deficiencies through resolution. Update Status as work progresses. Capture the date resolved and resolved-by initials for each item.
Item # | Location | Description | Trade | Priority | Status | Photo Ref | Identified | Resolved | Resolved By
Project: Suite 410 Fit-Out, 1200 Market Street - Substantial Completion 07/22/2026
001 | Conf Rm A (410.05) | Drywall not finished to Level 4 above ceiling cloud at south wall | Drywall | High | Open | IMG-0014 | 2026-07-22
002 | Open Office (410.10) | Two recessed downlights flickering at northwest workstations | Electrical | High | In Progress | IMG-0017 | 2026-07-22 |  | JM
003 | Kitchenette (410.20) | Sink P-trap leaking at slow drip; cabinet base water-stained | Plumbing | High | Open | IMG-0021 | 2026-07-22
004 | Office 410.07 | Door does not latch; strike plate misaligned by 1/8 inch | Doors and Hardware | Medium | Resolved | IMG-0024 | 2026-07-22 | 2026-07-29 | RT
005 | Reception (410.01) | Paint touch-up needed at three corners; roller marks visible under raking light | Paint | Low | Open | IMG-0028 | 2026-07-22
006 | Restroom 410.30 | ADA grab bar loose at one mounting; reseat per spec 10 28 13 | Specialties | High | In Progress | IMG-0031 | 2026-07-22 |  | BL
007 | Open Office (410.10) | Carpet seam visible at column line C; restretch and reseam | Flooring | Medium | Open | IMG-0034 | 2026-07-22
008 | Conf Rm B (410.06) | AV plate cover missing screws; loose against drywall | Low Voltage | Low | Open | IMG-0037 | 2026-07-22
009 | Corridor (410.99) | Ceiling tile damaged near sprinkler head; replace 2x2 tile | Ceilings | Medium | Resolved | IMG-0041 | 2026-07-22 | 2026-07-30 | JM
010 | Office 410.12 | Window blind missing; install per finish schedule | Window Treatment | Low | Open | IMG-0044 | 2026-07-22
011 | Pantry (410.20) | Outlet at appliance garage tests reverse polarity | Electrical | High | Open | IMG-0047 | 2026-07-22
012 | IT Closet (410.50) | Door undercut insufficient for return air | Doors and Hardware | Medium | In Progress | IMG-0050 | 2026-07-22 |  | RT
Template by BuildVision AI - buildvisionai.com - Generate this automatically with AI: https://buildvisionai.com

## How To Use
How to use the Punch List Template
1. | Walk the project with the Owner and Architect at substantial completion.
2. | Photograph every deficiency and reference the photo number.
3. | Assign each item to the responsible trade with a priority.
4. | Update Status weekly until all items are Resolved.
5. | Final completion is achieved when all punch list items are signed off.
Template by BuildVision AI - buildvisionai.com - Generate this automatically with AI: https://buildvisionai.com